## Week1
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1899237 |  |  | Week starting: | 1
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 3rd March | 12:00 | 17:30 | 5.5 | Read course outline, assessment overview, and project overview. Attempted to understand the course objectives, the learning outcomes for the first two weeks, and became familiar with the project topic. | Reviewing the course and project details ensures that all team members clearly understand the project's scope, objectives, and assessment criteria, which supports effective planning and preparation for upcoming milestones such as the Business Pitch and first prototype development. | Clearly understood the course objectives, early-stage deliverables, and assessment expectations. Gained a solid understanding of the project topic—AI-driven EEG analysis for cognitive load and engagement detection—enabling our team to begin preparing effectively for the Business Pitch and initial prototype planning.
Tuesday | 4th March | 13:00 | 14:00 | 1 | Reached out to team members via email to organize our initial group meeting. | This task facilitates effective team communication and coordination, critical for project initiation and successful teamwork throughout the project lifecycle. | Confirmed the first group meeting scheduled for the afternoon of March 5th.
Wednesday | 5th March | 15:00 | 17:30 | 2.5 | Participated in the first group meeting to introduce team members, outline initial project ideas, and schedule regular meeting times. | This initial meeting establishes foundational communication and collaborative norms, clarifies each member's expertise, and sets a consistent workflow necessary for structured project management. | Identified team members' technical backgrounds, scheduled the first client/supervisor meeting accommodating everyone's availability, and established routine group meeting schedule.
Thursday | 6th March | 10:30 | 15:00 | 4.5 | Reviewed the Agile Software Engineering Methodology and familiarised myself with GitHub's Project Management tools. | Understanding Agile methodology and GitHub project management ensures our project management and development processes align with industry-standard best practices, supporting efficient collaboration and timely project progression. | Acquired foundational knowledge of Agile methodology principles, including iterative development, continuous improvement, and adaptive planning. Also gained proficiency in utilising GitHub for task tracking, collaborative coding, and version control to enhance team productivity.
Friday | 7th March | 14:00 | 15:30 | 1.5 | Discuss with group members to confirm the routine Group Sprint Meeting time. | Establishing regular Sprint meeting times ensures consistent communication, facilitates ongoing progress updates, timely identification of issues, and effective coordination of tasks according to Agile principles, thus maintaining the project's momentum. | Set provisional routine Group Sprint Meeting times on Mondays (16:00 - 17:00) and Fridays (16:00 - 17:00). Monday meetings will serve as Sprint Planning Meetings, while Friday meetings will function as stand-up meetings to track progress and address any immediate concerns.
Saturday | 8th March | 10:00 | 16:00 | 6 | Conducted research on Brain-Computer Interface (BCI) application areas and reviewed recent studies and current real-world BCI applications. | This research helps the team understand the broader context and latest developments in BCI technology, which is essential for identifying best practices, potential challenges, and innovative opportunities relevant to our EEG-based cognitive load and engagement detection project. | Gained comprehensive insights into various BCI applications, including healthcare, education, gaming, and assistive technology. Identified promising use cases and methodologies that can inform our approach. Next action is to narrow down specific strategies suitable for our project's objectives.
Sunday | 9th March |  |  | 0
|  |  | Total | 21

## Week2(unfinished)
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1899237 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 10th March | 8:00 | 16:00 | 8 | Conducted online research on the FLEX 2 Gel - 32 Channel Wireless EEG Head Cap System, the EEG capturing device for this project. Searched official and reliable online sources to understand device functionality and the types of data it captures. | This task contributes to gaining essential background knowledge about the primary hardware used in our project, ensuring we understand its capabilities and limitations, which is crucial for accurate data acquisition and analysis. | Outcome 1: The device uses Bluetooth wireless technology to transmit EEG data, minimising noise interference typically associated with wired connections, thus potentially enhancing signal quality. Outcome 2: Research samples of EEG data were found, indicating that they are presented as multi-channel numeric data streams. Outcome 3: The wireless nature of the EEG device can significantly aid in artefact removal by reducing mechanical and movement-related noise, leading to cleaner and more reliable EEG signals for analysis.
Tuesday | 11th March | 12:00 | 15:00 | 3
Wednesday | 12th March | 8:00 | 10:00 | 2
Thursday | 13th March |  |  | 0 | Client/Supervisor Meeting. |  | Discussed with client/supervisor and got a general idea of the project scope.
Friday | 14th March |  |  | 0
Saturday | 15th March |  |  | 0
Sunday | 16th March |  |  | 0
|  |  | Total | 13

## Week3(unfinished)
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1899237 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 17th March |  |  | 0
Tuesday | 18th March | 12:00 | 15:00 | 3
Wednesday | 19th March | 8:00 | 10:00 | 2
Thursday | 20th March |  |  | 0
Friday | 21st March |  |  | 0 | Group Meeting to disscuss task Allocation for the Pitch presentation. Go through User Story and all the use cases. Disscuss the format of the presentation. We discuss about the Q&A session in the Pitch presentation. To discuss the functionalities, user story, and use case of the final product we shall deliver for our next milestone. |  | We have our tasks divided into several parts based on the structure of the presentation we have came up. We have discussed and confirmed the final product we are going to deliver will be a Brain-controlled Text Reader. We have disscussed and confirmed that the milestone one for this project will be a Minimum Viable Product (MVP) version of this Brain-controlled Text Reader. The functionalities of this product will include 1. EEG Device Wearing and Adjustment Guideline 2. Mind-Controlled Instructions Training 3. Book page control by Mind-Controlled Instructions. We have discussed and confirmed the parts allocation of the Pitch Presentation: 1. (Guanhua's part) Intro/Background, Storyline, and Motivation. 2. (Yufei's part) Introduction about our BCI solution (Brain-controlled Text Reader) to the existing problems. 3.(Zebang's part) Software Architecture. 4. (Gengchao's part) Flowchart with timeline and milestone, intro about Agile 5. (Haomin's part) Team member allocation, roles played. Future Development. We have confirmed that the Q&A session will be hold on another meeting with our client/supervisor with one question for each member.
Saturday | 22nd March |  |  | 0 | Read Emotiv official API documentation. |  | Got overview understanding of the Cortex API.
Sunday | 23rd March |  |  | 0 | Read Emotiv official API documentation. Apply for Emotiv Developer Secret Key, App_Name, App_ID, Client_ID for later use. Brainstorming on the name of our product and decide an ear-catching product name with group members. Write backend Architecture. Study how to rename my name on githb as contributors, and rename my name on github for the past commit record. |  | Successfully get and ducumented the Cortex Client secret key, App_Name, App_ID, Client_ID. The product name will called "NeuroFlip Reader". Provisionaly, we decide to use Python Flask Framework as Backend development language, React as Front End development language. we use WebSocket to connect backend and frontend. We use Cortex API service to communicate with Emotiv Headset. We will use SQLite to store user profile and credentials locally. Successfully setup the github contributor's name and email as the Uni id and Uni email.
|  |  | Total | 5

## Week4 Plan
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1899237 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 24th March |  |  | 0 | Practice presentation
Tuesday | 25th March | 12:00 | 15:00 | 3
Wednesday | 26th March | 8:00 | 10:00 | 2
Thursday | 27th March |  |  | 0
Friday | 28th March |  |  | 0
Saturday | 29th March |  |  | 0
Sunday | 30th March |  |  | 0
|  |  | Total | 5

## Template
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1899237 |  |  | Week starting: | 1
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  |  |  | 0
Tuesday | 4th March | 12:00 | 15:00 | 3
Wednesday |  | 8:00 | 10:00 | 2
Thursday |  |  |  | 0
Friday |  |  |  | 0
Saturday |  |  |  | 0
Sunday |  |  |  | 0
|  |  | Total | 5