## Sheet2
MCI Project Weekly Time Sheet
Team | LY1 | Student ID |  | a1904674 |  | Week starting: | 2025-03-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-17 | 11:00 | 15:00 | 4 | Organized weekly team meetings every Monday to align project progress and team understanding, standardize user stories, and initially divide the project into task modules based on the current understanding. | promoted efficient collaboration, generated initial user story, defined the task modules. | Initial user story generated, ensured all members understand their roles.
Tuesday | 2025-03-18 | 11:00 | 15:00 | 4 | Adusted the Emotiv EEG device, analyzed the BCI interaction logic, and collected preliminary user EEG data to verify device functionality and interaction flow. | Early data collection, identified potential issues in signal quality and user interaction patterns. | Evaluate data quality and signal stability
Wednesday | 2025-03-19 | 10:00 | 15:00 | 5 | Studied the official Emotiv API to assess integration complexity and functional limitations, providing technical groundwork for future development. | Understanding the capabilities and constraints of the API | Identify any potential limitations or required efforts
Thursday | 2025-03-20 | 10:00 | 18:00 | 5 | Held weekly meetings with the supervisor to raise current uncertainties, submitted user stories for review, and received constructive feedback to refine project direction. | ensured timely clarification of issues and alignment with project goals. Improved user story quality and guides further planning and development. | Update user stories, Apply feedback to adjust task priorities and development focus
Friday | 2025-03-21 | 10:00 | 18:00 | 8 | Held two meetings: 1. Refined user stories based on supervisor feedback and drafted a detailed outline for next week's presentation pitch. 2. Categorized existing project content and assigned specific tasks to each team member to ensure steady progress. | Provides a structured platform for task tracking, collaboration, and project transparency. | Project management system is in place, and team members have access to key project details.
Saturday | 2025-03-22 | 13:00 | 17:00 | 4 | Prepared the technical architecture section of the presentation pitch slides, clearly outlining the overall system structure and key technological components. | supported internal alignment on architecture decisions. | Compeleted technical slides part. Prepare to explain technical choices during the pitch session
|  |  | Total | 30