## Sheet2
MCI Project Weekly Time Sheet
Team | LY1 | Student ID | a1911139 |  |  | Week starting: | Week 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-10 | 16:00 | 19:00 | 3 | Internal meeting on Teams: Discuss project management methods and schedule, collect questions for supervisor. | Project management setup and alignment, organizing tasks for the upcoming work. | Prepare questions for supervisor for next meeting.
Tuesday | 2025-03-11 | 11:00 | 17:00 | 6 | Research on previous EEG studies in BCI; explore existing software for EEG analysis. | Gaining knowledge of EEG data analysis and best practices. | Summarize findings and create a presentation for Thursday.
Wednesday | 2025-03-12 | 11:00 | 15:00 | 4 | Review and compare different BCI models and methodologies for data collection. | Understanding different methodologies to lay foundation for our practice. | Choose the best approach for EEG data collection and finalize tools for Thursday.
Thursday | 2025-03-13 | 10:00 | 15:00 | 5 | Meeting with supervisor: Supervisor introduced the project and gave us the experiment headset. | Introduction to the hardware and initial review of project goals. | Set up the experiment for testing and prepare for testing.
Friday | 2025-03-14 | 16:00 | 20:00 | 4 | In-person internal meeting: Test the headset, discuss user requirements, and define functions to be realized. | Testing the EPOC+ headset and analyzing how BCI fits into the user requirements. | Organize user requirements and begin creating test cases for the headset functionalities.
Saturday | 2025-03-15 | 11:00 | 16:00 | 5 | Investigate software tools for EEG signal processing and begin designing experiment tasks. | Learning about software integration for EEG data analysis and designing experiments. | Start developing the experiment structure and prepare materials for the upcoming tests.
|  |  | Total | 27